## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US001 | Implement image/video upload module and validate user input | MUST HAVE | Streamlit | Gaurav Kumar | 3- Completed
S1 | S1 | US002 | Integrate YOLO model for automatic number plate detection | MUST HAVE | Python Libraries, Ultralytics | Gaurav Kumar | 3- Completed
S1 | S1 | US003 | Apply OCR to extract text from detected number plates | MUST HAVE | Easy OCR | Gaurav Kumar | 3- Completed
S1 | S1 | US004 | Display ANPR results and generate downloadable CSV output | MUST HAVE | US003 | Gaurav Kumar | 3- Completed
S2 | S2 | US005 | Integrate YOLO ATCC model to detect traffic objects | MUST HAVE | Python Libraries, Ultralytics | Gaurav Kumar | 3- Completed
S2 | S2 | US006 | Implement automatic traffic counting and classification logic | MUST HAVE | US005 | Gaurav Kumar | 3- Completed
S2 | S2 | US007 | Create CSV summary for ATCC results | MUST HAVE | US006 | Gaurav Kumar | 3- Completed
S3 | S3 | US008 | Develop integrated dashboard for ANPR + ATCC in Streamlit | MUST HAVE | Streamlit UI | Gaurav Kumar | 3- Completed
S3 | S3 | US-009 | Optimize model performance and reduce inference delay | MUST HAVE | YOLO Models | Gaurav Kumar | 3- Completed
S4 | S4 | US-010 | Improve final UI/UX and add navigation between ANPR and ATCC | MUST HAVE | Streamlit | Gaurav Kumar | 3- Completed
S4 | S4 | US-011 | Prepare final deployment-ready version | MUST HAVE | All previous tasks | Gaurav Kumar | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 52 | 5 | 9 | 12 | 12 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TASK-001 | Create Streamlit upload module (image/video support) | 2025-11-01 | 2025-11-02 |  | Build | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-002 | Integrate YOLO model for number plate detection | 2025-11-02 | 2025-11-05 |  | Model Integration | 3- Completed | 6 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-003 | Perform OCR to extract plate text | 2025-11-05 | 2025-11-07 |  | OCR Processing | 3- Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-004 | Display ANPR results + generate CSV file | 2025-11-07 | 2025-11-10 |  | Data Output | 3- Completed | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG (ATCC Model Integration)
US-005 | TASK-005 | Integrate YOLO ATCC model (car/bus/bike detection) | 2025-11-11 | 2025-11-14 |  | Model Integration | 3- Completed | 6 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TASK-006 | Implement object counting + class-wise categorization | 2025-11-14 | 2025-11-17 |  | Logic Development | 3- Completed | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TASK-007 | Create CSV export functionality for ATCC | 2025-11-17 | 2025-11-20 |  | Data Output | 3- Completed | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG (Final Dashboard + Optimization)
US-008 | TASK-008 | Build combined ANPR + ATCC Streamlit dashboard | 2025-11-21 | 2025-11-26 |  | UI/Frontend | 3- Completed | 8 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TASK-009 | Model performance optimization (reduce latency) | 2025-11-26 | 2025-11-30 |  | Optimization | 3- Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG (Deployment + Final Polishing)
US-010 | TASK-010 | Final UI polishing & bug fixes | 2025-12-01 | 2025-12-05 |  | Coding | 3- Completed | 6 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TASK-011 | Final deployment + documentation | 2025-12-05 | 2025-12-10 |  | Deployment | 3- Completed | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | Difficulty installing YOLO & OCR libraries | Discussed with mentor; installed correct Ultralytics + EasyOCR versions
S1 | Day 7 | Low accuracy in number plate OCR | Applied image preprocessing (grayscale, thresholding) based on mentor suggestion
S2 | Day 14 | ATCC model failing to classify small/distant vehicles | Adjusted confidence threshold + NMS; mentor shared sample configs
S2 | Day 18 | Counting logic mismatch when vehicles overlapped | Debugged with mentor; added object tracking (ID-based counting)
S3 | Day 25 | Dashboard UI layout breaking during integration | Mentor guided UI restructuring using Streamlit columns
S4 | Day 35 | Difficulty preparing final deployment documentation | Conducted mentoring session; documentation completed and validated

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-01 | 2025-11-10 | Gaurav Kumar | Start maintaining daily logs for progress tracking | Stop delaying environment setup | Continue learning model basics | Completed installation & setup of YOLO, Tesseract, Streamlit
2 | S2 | 2025-11-11 | 2025-11-20 | Gaurav Kumar | Start experimenting with model thresholds & parameters | Stop debugging without break (reduced productivity) | Continue experimenting with ATCC model | Improved classification accuracy with threshold tuning
3 | S3 | 2025-11-21 | 2025-11-30 | Gaurav Kumar | Start organizing UI elements from beginning | Stop ignoring minor UI issues | Continue refining dashboard | Created a clean, user-friendly combined ANPR + ATCC dashboard
4 | S4 | 2025-12-01 | 2025-12-10 | Gaurav Kumar | Start writing documentation regularly | Stop leaving deployment for last day | Continue reviewing code quality | Successfully deployed final solution & submitted documentation
5
6
7