## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Gaurav Kumar | 2025-11-03 | File upload failed for large MP4 videos | S1 | Gaurav Kumar | Logical | Added max file size handling & improved validation | 2025-11-04 | Closed | Working fine after fix
2 | Gaurav Kumar | 2025-11-06 | YOLO ANPR model not detecting angled plates | S1 | Gaurav Kumar | Standards | Updated model config + enabled rotation augmentations | 2025-11-05 | Closed | Detection accuracy improved
3 | Gaurav Kumar | 2025-11-08 | OCR reading incorrect characters on blurred plates | S1 | Gaurav Kumar | Logical | Applied preprocessing (denoise, threshold) before OCR | 2025-11-06 | Closed | OCR readability improved
4 | Gaurav Kumar | 2025-11-15 | ATCC model misclassifying bicycles as motorcycles | S2 | Gaurav Kumar | Maintainability | Adjusted class confidence thresholds + retrained small dataset | 2025-11-07 | Closed | Classification now stable
5 | Gaurav Kumar | 2025-11-18 | Overlapping vehicles counted twice | S2 | Gaurav Kumar | Logical | Integrated object tracking (ID-based counting) | 2025-11-08 | Closed | Counting now accurate
6 | Gaurav Kumar | 2025-11-27 | Dashboard UI alignment breaks when switching modules | S3 | Gaurav Kumar | User Interface | Redesigned layout using Streamlit columns + spacing | 2025-11-09 | Closed | UI stable on all screens

## Sheet2
Logical
User Interface
Maintainability
Standards
Others